**APPENDIX**

**Project Timeline, Milestones, and Outcomes**

The projected timeline below delineates milestones and outcomes for (a) overall organization and collaboration of team members, (b) Objective 1, and (c) Objective 2.

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Year 12019 | Year 22020 | Year 32021 | Year 42022 | Year 52023 |
| **Organization and Collaboration of Team Members**  |  |  |  |  |  |
| * Elect executive committee
 | X |  | X |  | X |
| * Hold executive committee and working group conference calls
 | X | X | X | X | X |
| * Hold an annual research team meeting
 | X | X | X | X | X |
| * Submit state reports
 | X | X | X | X | X |
| **Objective 1: Community Capacity** |  |  |  |  |  |
| * Identify public data sources for community-level data
 | X |  |  |  |  |
| * Identify target counties based on public data
 | X |  |  |  |  |
| * Develop strategies for collecting community-based data
 | X |  |  |  |  |
| * Train team members in community data collection methods
 |  | X |  |  |  |
| * Collect community data
 |  | X |  |  |  |
| * Create a multistate community dataset
 |  | X |  |  |  |
| * Develop community stake holder protocol
 |  | X |  |  |  |
| * Train team members in conducting community stake holder interviews
 |  | X |  |  |  |
| * Interview community stakeholders
 |  | X |  |  |  |
| * Transcribe and analyze community stake holder interviews
 |  | X |  |  |  |
| * Prepare community profile reports for community stakeholders
 |  |  | X |  |  |
| * Conduct a comparative analysis of communities
 |  |  | X |  |  |
| **Objective 2: Individual and Family Resiliency** |  |  |  |  |  |
| * Explore existing NC1171 quantitative and qualitative data to understand individual, family, and community resiliency factors and processes and to identify constructs to include in the new data collection
 | X |  |  |  |  |
| * Finalize quantitative surveys
 |  | X |  |  |  |
| * Develop case study interviews
 |  | X |  |  |  |
| * Finalize sampling plan for each state
 |  | X |  |  |  |
| * Train team members to collect survey and/or case study data
 |  |  | X |  |  |
| * Collect survey data
 |  |  | X |  |  |
| * Identify and invite a subgroup of mothers to participate in case study
 |  |  | X |  |  |
| * Conduct case study interviews
 |  |  | X |  |  |
| * Analyze case study interviews
 |  |  |  | X |  |
| * Create a combined quantitative dataset including community and survey data
 |  |  |  | X |  |
| * Analyze quantitative data
 |  |  |  | X | X |
| * Disseminate findings to diverse audiences
 |  |  |  |  | X |