**APPENDIX**

**Project Timeline, Milestones, and Outcomes**

The projected timeline below delineates milestones and outcomes for (a) overall organization and collaboration of team members, (b) Objective 1, (c) Objective 2, and (d) Objective 3.

|  | **Year 1****2024** | **Year 2****2025** | **Year 3****2026** | **Year 4****2027** | **Year 5****2028** |
| --- | --- | --- | --- | --- | --- |
| **Organization and Collaboration of Team Members**  |  |  |  |  |  |
| Elect executive committee | X |  | X |  | X |
| Hold executive committee and working group conference calls | X | X | X | X | X |
| Hold an annual research team meeting | X | X | X | X | X |
| Submit state reports | X | X | X | X | X |
| **Objective 1: Family system sustainability** |  |  |  |  |  |
| Data processing, cleaning, and organization | X |  |  |  |  |
| Conduct preliminary analyses  | X | X |  |  |  |
| Form working groups | X | X | X |  |  |
| Analyze family data  | X | X | X | X | X |
| Integrate family data with community data |  |  | X | X | X |
| Disseminate research findings to diverse audiences |  | X | X | X | X |
| **Objective 2: Sustainable system-to-system interactions** |  |  |  |  |  |
| Identify and access datasets from national preparedness agencies to gain perspective on family resilience in community contexts | X |  |  |  |  |
| Workgroup to compile dataset from national data for comparison with family and community data previously collected (2019-2024) | X | X |  |  |  |
| Comparative analyses of NC1171 family data and national datasets to contextualize rural family data | X | X | X | X | X |
| Comparative analyses of NC1171 Community Key Informants data and national datasets to further contextualize rural family data | X | X | X | X | X |
| Research findings will be compared to broader rural family research literature to inform best research-to-family-practice strategies |  | X | X | X | X |
| Disseminate research findings to diverse audiences |  |  |  |  |  |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | **Year 1****2024** | **Year 2****2025** | **Year 3****2026** | **Year 4****2027** | **Year 5****2028** |
| **Objective 3:** **Sustainable Systems Recommendations** |  |  |  |  |  |
| Identify and recruit Advisory Council (AC) Members | X |  |  |  |  |
| Hold AC meetings and gain feedback from membership | X | X | X | X | X |
| Apply for additional funding to support Objective 3 incentives for needs assessment, evaluation, and lived experience experts | X | X |  |  |  |
| Develop protocol and procedures, including IRB, for survey of rural family-serving professional needs assessment and evaluation | X |  | X |  |  |
| Collect data from rural family-serving professional through surveys and webinar discussions |  | X |  |  |  |
| Analyze family-serving professional data and revise *Relying on Rural Resilience (RRR)* delivery and/or content as indicated |  | X | X |  |  |
| Offer quarterly *RRR* virtual professional development series | X | X | X | X | X |
| Develop *RRR* series outcomes and impact indicators for participants and presenters |  | X | X |  |  |
| Collect evaluation data from *RRR* series participants and presenters | X | X | X | X | X |
| Develop best practice for sustainable resilience within rural families or their supporting systems for use by current and future rural family-serving professionals |  | X | X | X | X |
| Disseminate research findings to diverse audiences |  | X | X | X | X |