NCERA 197

Agricultural Safety and Health Research and Extension Coordinating Committee

Agricultural Equipment on Public Roads White Paper Sub-Committee

December 18, 2007

Conference Call Minutes

Attendees: Dennis Murphy – chairperson (Penn State), Marshall Martin – Administrative Advisor (Purdue), Bob Aherin (Univ Ill), Dee Jepsen (Ohio State), Karen Hunter (CSREES-USDA), Connie Baggett (Penn State), Chuck Schwab (Iowa State), Bobby Grisso (Virginia Tech), Aaron Yoder (Penn State)

The meeting was called to order at 1:30 pm EST by Dennis Murphy with a welcome and participants introduced themselves.

Progress report on 1st or 2nd draft, reactions from participants

- Papers were submitted by the High Speed Tractor group and the Horse Drawn Vehicle group.

- Murphy reported on the Horse Drawn Vehicle group

  - No feedback was given from the group

  - Still trying to contact Purdue and Ohio State

  - Have obtained a copy of proposed ASABE standard

  - Have obtained national FARS data, which appears to have a low number of incidents

  - Working on obtaining state stats for PA, OH and IN

- Grisso reported on the High Speed Tractor group

  - Not much response from the group

  - He is seeking help from industry regarding tires – no responses

  - Has investigated the format of white papers from ASABE.

    - Short Problem Statement

    - Recommendations

    - Background

  - Will forward format examples to Murphy

- Aherin reported on the Lighting and Marking group

  - They are investigating

    - Evolution of the standard

    - Special Populations

    - State Stats

    - Roadway Crashes

    - Retrofitting

    - Misuse of SMV

    - High Speed Equipment

    - Pro’s and Con’s of National Standardization

  - They will have a draft in January

- A clarification was made that all of these drafts will be merged into one white paper, not multiple papers.

- Baggett reported on the Licensing of Drivers group

  - Is researching DMV’s in different states to summarize

  - Was alerted to a JASH article from Marlenga in Wisconsin

- Schwab reported on the Rural / Urban Interface group

  - Added Carol Lehtola, Herb Wilcut and Brian Hammer to his group

  - Has obtained access to the Iowa DOT database

  - Has a first draft out to his committee

Identify outside reviewers

- Holding off until future date

- Gary Erisman has volunteered

Review timeline and next steps

- March 1 – all final section drafts are due to Murphy

- March 31 – combined draft out to committee for review

- April 18 – all comments on combined draft due to Murphy

- April 24-25 – face to face meeting in Washington DC – Brad/Karen to get room. Write a common introduction, identify overlap, rewrite as needed.

AETC Conference Presentation

- Murphy will be presenting information on this process in mid-February. He will have 20-25 minutes for the presentation.

- He will be asking for reviewers

ASABE Posters

- The three poster abstracts have been submitted and accepted. Will b e display on Monday or Tuesday afternoon

- ESH poster session will not conflict with ESH paper sessions

- Other posters in ESH are welcome

NIFS Professional Development Session

- We have 3-4 hours for the session

- We should review major sections of the paper (possibly in groups/expert panels), including development of research questions (several will be included in the draft document)

- We might want to use a panel discussion format to:

  - Prioritize areas of work

  - Develop alternate/opposing view points

- Use feedback from panel/group discussions for finalizing paper

- Ask for additional reviewers for final paper.

- Need to be sure we include discussion on why we chose this topic to develop a white paper, and the process we used.

  - Should we write white papers on all the NCERA 197 priority topics?

Conference call ended approximately 2:30 pm EST.

Aaron Yoder, Recorder