Day 1:	May 27, 2010

- Welcome by host Ryan Boyles, followed by a brief presentation on climate

- Scott Staggenborg appointed as acting chair for the meeting due to the absence of Adnan Akyuz

- Brief introductions and welcome of new members

- Comments by Administrative Advisor Mike Schmitt

  - Emphasis on products and outcomes for Multi-state Research Groups, such as the atlas project of NC-1018, workshops, grants, etc.

  - Multi-state projects provide a great value to the participating universities

  - Formula funds versus capacity building funds

  - NIFA funding ranges from broad to target based

- Climate Atlas

  - Project was initiated many years ago

  - Due to retirements of various participants not much progress has been made

  - NCRA had provided funding for completion and to print a book

  - Money was returned to NCRA due to lack of activity

  - An electronic copy can be retrieved from a web site housed at Iowa State University

  - Group agreed to discontinue the hard copy project

- Status of action items of the NC-1018 2009 annual meeting

  - Action 1: Dennis to work with Steve H and Ken H to see if MRCC database can be acquired: Open

  - Action 2: Dennis to work with Pat and Ken H to determine what additional variables can be added to the database: Open

  - Action 3: Scott to contact UCSB and Rich to contact Noah Diffenbaugh to pursue completing 2009 milestone (Develop a framework for testing or creating a new climatology based on climate change prediction scenario): Closed, no prospect.

  - Action 4: To pursue fulfilling objectives 1-c “to enhance current NC-1018 database with climate data that will be developed based on climate change protection models:” Closed due to closing of Action 3.

  - Action 5: Meet during NC-1018 meeting to discuss finalizing the text of the Atlas. Closed.

  - Action 6: Dennis to talk to Daryl to see if he can add the atlas, the proposal and the minutes to the web site: Completed.

  - Action 7: Adnan will type and distribute the minutes within 60 days of the meeting: Completed.

  - Action 8: Project termination report to be submitted by March 31, 2010: Completed.

  - Action 9: Ken to talk to Steve Hilberg to see if MRCC would be willing to provide continues data feed to NC-1018 database: Open.

  - Action 10: Jeff to talk to Steve Hollinger and Dennis to talk to Stew and Daryl to see if they would be willing to continue service to complete the Atlas: Open.

  - It was decided to close the Open Action items 1, 2, 9 and 10.

- Action Item:

  - Explore if the MRCC is willing to host the NC-1018/NC-1179 database.

- Regional Climate Center Reports

  - HPRCC has a new director, Dr. Martha Shulski

- State Climate Reports

  - Kansas: Scott Staggenborg, John Holman, and Mickey Ransom

  - New York: Bob Seem

  - Nebraska: Steve Hu

  - Georgia: Gerrit Hoogenboom

  - Montana: Perry Miller

  - Florida: Clyde Fraisse

Day 2:	May 28, 2010

- AFRI Proposal; pre-proposal developed by Scott Staggenborg; discouraged from submission of a full proposal

- Open AgroClimate:

  - Opportunities for adoption by other states; prototypes are currently in operation in New Mexico and Paraguay

  - See www.Open.AgroClimate.org for further information

  - A workshop is planned on Open AgroClimate during the upcoming CIMR Conference, scheduled for May 24 – 27, 2011; www.conference.ifas.ufl.edu/cimr/

  - The Open Source activities by ZedZ were discussed

- Business Meeting

  - Proposal to meet with the WERA 102 was discussed. The meeting with WERA 201 in Fort Collins several years ago was very successful. However, timing seems to be an issue

  - E-mail via the listserver established at Iowa State University is successful.

  - There was a discussion to expand the group with additional members:

    - Jeff Andresen to continue as a member

    - To invite John Antle and Susan Capalbo, Agricultural Economists at Oregon State University

    - To invite Victor Cabrera, Livestock specialist at the University of Wisconsin

    - To invite Brenda Ortiz, Extension Agronomist at Auburn University

  - Leadership

    - Adnan Akyuz will continue as chair

    - Gerrit Hoogenboom announced that he will step down as secretary due to a change in his position (move to Washington State University)

    - Clyde Fraisse elected as secretary

- Project Planning

  - Objectives

    - Enhance the understanding of crop-climate-soil interaction at a regional scale

    - Application of risk assessment tools, including the NC-1018 database , for the crop-climate-soils interface on  regional scale

    - Enhance the understanding of potential bioenergy production systems

    - Disseminate the research outcomes on the potential effects of climate variability and climate change effects on crop production resource use and adaptation options to users and stakeholders

  - Outputs

    - Projections of climate change impacts on food, feed, fuel and fiber crops

    - Potential options for adaptation

    - Bioenery crops and cropping systems

  - Models and data

    - Weather data appropriately downscaled

      - Max and min temperature, solar radiation, precipitation, relative humidity, wind and leaf wetness

      - Resolution, spatial and temporal

      - Statistical downscaling

    - Crop models

      - Downscaled weather data

      - Soil

      - Crop management

    - Crops

    - Pests

      - Under development

    - Economics

      - Trade off analysis – Oregon State involvement

    - States

      - NC-94/NC-1018/NC-1179

        - North Dakota, South Dakota, Kansas, Minnesota, Indiana, Missouri, Wisconsin, Michigan, Illinois

      - Southeast Climate Consortium

        - Florida, Georgia, Alabama, North Carolina

- Action Items

  - Climatologists report in 6 months on available data or preferred methodologies to generate downscaled data with details on spatial and temporal resolution and available variables

  - If the climatologists fail to provide data an alternative is to look at the data available from NARCCAP where currently outputs from four models have been processed (www.narccap.ucar.edu).

  - Evaluation of crop simulation models

    - Wheat: Perry Miller

    - Forage sorghum: Scott Staggenborg

    - Need for soybean and maize for the Midwest

    - Soybean and maize for the southeast: graduate student under the supervision of Gerrit Hoogenboom

- Meeting adjourned at noon

  - Vote of thanks for Ryan Boyles for hosting the meeting